## Slide 1
Sample Format: Unit Training Event
The standard military 8-Step Training Model provides leaders with an effective method to design, execute, and asses all annual training events; from the individual to the unit.
This company uses the format in the pages below to give leaders a standard operating procedure for developing, executing and assessing training events.
These training event packets may include additional training documents depending on the complexity of the event (e.g. risk assessment sheet, medical evacuation sheet, observer sheets, maps, grading sheets, exam sheets, training operation orders, opposing force guidance).
The leader(s) assigned as the project managers for each training event will regularly brief the commander and executive officer on the planning and resource status using this product as a guide for briefing.
This example format depicts a unit that is planning a squad collective training event.
COMPANY TRAINING EVENTS (FM 7-0, Appendix E)
E-30. Training events <are> managed using the T-Week framework. This is a planning technique that identifies actions and activities to accomplish prior to each training event. T-Week is the week of training execution; T-6 represents activities six weeks prior to execution. … Units develop and tailor their own T-week actions and timelines based on local command and installation requirements…
T-16 Identify major training facilities
Week T-12 Conduct training event planning
Week T-11 Refine event requirements
Week T-10 Begin pre-execution checks
Week T-9 Confirm resource requests
Week T-8 Execute reconnaissance and confirm resources
Week T-7 Publish the training event orders
Week T-6* Review and complete deliberate risk assessments
Week T-5 Complete tactical plan and supporting products
Week T-4 Conduct certifications and complete prerequisite training
Week T-3 Conduct rehearsals
Week T-2 Finalize support and conduct OPFOR rehearsal
Week T-1 Draw equipment or supplies and execute subordinate rehearsals and checks
T Week Execute training
Week T+1 Recover, and conduct final after action reviews
*Training schedule approved and published at T-6

## Slide 2
LT Steel
SFC Slaughter
Virtual. 18-21FEB56
Field. 24FEB-01MAR56
Virtual: SAM-T
Field. Ranges 53-54
IN MECH Company, SAM-T Virtual Trainer, Range 53-54.
Squads successful completion of virtual, situational and live exercises IAW doctrine and SOP.
1 PLAN | 02DEC19-17JAN56
2 TRAIN TRAINERS | 04-06FEB56
3 RECON SITE | 17JAN56, 13FEB56
4 PUBLISH-BRIEF | 17JAN56
5 REHEARSAL(S) | 12-13FEB56
6 TRAIN | 18-29FEB56
7 AAR | 29FEB56
8 RETRAIN | 29FEB56
1 CRM | COMPLETE
2 RESOURCING | COMPLETE
3 IMAGERY SHEET(S) | COMPLETE
4 TIMELINE | COMPLETE
5 TROOP TO TASK | COMPLETE
6 AAR GLIDEPATH | COMPLETE
123-23-22A3.
(Conduct Troop Leading Procedures)
123-24-22A4.
(Issue an Operations Order)
123-24-22A5.
(Conduct Leader’s Reconnaissance)
123-24-22A6.
(Conduct a Squad Attack)
123-24-22A7.
(Conduct a Squad Defense)
02DEC55 – 17JAN56
24 0900 FEB 56 (Field)
24-29FEB56 (Field)
01 1500 FEB 56 (Field)
04 1500 FEB 56
AS OF DATE: 15JAN56
Conduct Squad Situational and Live Fire Exercises 10FEB-01MAR56.
SQUAD: SITUATIONAL TRAINING EXERCISE (STX) // LIVE FIRE EXERCISE (LFX)
Training Summary Sheet.
This page is the summary sheet and outlines all major dates, responsible persons, major timelines, task/purpose, and area of operations. This page can also include reference to publications that provide guidance specific to the training event.

## Slide 3
TYPE | QUANTITY
Z0XX BLANK SAW | 8,000
Z0XX BLANK 5.58 | 10,400
Z0XX BLANK 7.66 | 8,000
Z0XX GREEN SMK | 30
Z0XX YELLOW SMK | 30
Z0XX RED SMK | 4
Z0XX VIOLET SMK | 30
Z0XX TNG SMK | 25
Z0XX W STR CLUST | 28
Z0XX SIM GRND | 100
Z0XX SIM HG | 70
Z0XX SAW 4/1 | 6,400
Z0XX 7.66 4/1 | 6,400
Z0XX 5.58 | 8,400
Z0XX 37MM PRAC | 200
Z0XX AT-7 | 4 AND 4
2 MAN TEAM WILL BE ATTACHED TO THE COMPANY DURING THIS OPERATION TO WORK ON WHEELED AND TRACKED VICS. ADDITIONAL COORDINATION WILL BE RESOURCED THROUGH THE SENIOR MECHANIC SFC FLAPPY.
24FEB- M/A
25-28FEB- A/M/A
01MAR-A/M
FUEL RESUPPLY SCHEDULED FOR 26FEB20. COORDINATION FOR RESUPPLY WILL BE THROUGH COMPANY XO. COMPANY XO WILL COORDINATE THROUGH FSC DISTRIBUTION TO PROVIDE SCHEDULED AND UNSCHEDULED CLIII RESUPPLY.
C-WIRE/PICKETS AVAILABLE AND WILL BE ON-SITE TO AUGMENT ENEMY DEFENSIVE POSITIONS.
COMPANY XO WILL COORDINATE WITH COMPANY SUPPLY AND COMPANY HQ TO ENSURE DELIVERY AND RETURN OF CLIV.
SQDS WILL REST AFTER THEIR INDIVIDUAL LANES. THEY WILL BE AFFOREDED AMPLE TIME TO EAT. PORT-A-POTTIES WILL BE ON SITE FOR HUMAN WASTE,
WEATHER WILL BE CONSTANTY MONITORED. BURN BARRELS HAVE BEEN REQUESTED AND WILL BE USED DURING INCLEMET WEATHER. NO DIGGING IS PERMITTED FOR THIS EXERCISE. WHEN AUTHORIZED, WARMING PITS CAN BE SUSTAINED WITH NO DISTURBANCE TO LIVE VEGETATION.
AS OF DATE: JAN56
SQUAD: SITUATIONAL TRAINING EXERCISE (STX) // LIVE FIRE EXERCISE (LFX)
MEDICS WILL CARRY ALL CL VIII ON-SITE. RESUPPLY WILL BE COORDINATED THROUGH THE COMPANY XO BY REQUEST. COMPANY XO WILL COORDINATE WITH SENIOR MEDIC AND BN MEDICAL PLT FOR RESUPPLY TO COMPANY.
MEDICAL PERSONNELL WILL BE ON GROUND WITH THE CO. SQUADS WILL HAVE THEIR PLT MEDIC WALKING LANES WITH THEM. MEDICAL CP WILL BE COLLOCATED WITH THE COMPANY CP (78S PK 25870 43083).
Training Resource Sheet.
This page is the summary resource sheet and outlines all major resources that will be required for the training event.
See FM 7-0, Appendix E for additional ways units track training resources.
Notes: Bunker (provided by Range Control)
C-Wire for Bunker Obstacle & Route Obstacle
SIT Tgts (provided by Range Control)

## Slide 4
INDIVIDUAL-TEAM TRAINING (IWTS TABLE I) MACRO
10FEB56 (MON):
PRT
Command Maintenance
Leader/OC Azimuth Check
OPORD (19FEB56 Operation) Release
Platoon Leader Back-briefs
11FEB56 (TUE):
PRT
Fire Team Maneuver Training
Squad Communication Training
Squad Reporting Training
Platoon-Squad OPORD Training
12FEB56 (WED):
PRT
Fire Team Maneuver Training
Squad Communication Training
Squad Reporting Training
Platoon OPORD
Squad Leader Back-briefs
13FEB56 (THU):
PRT
Leader/OC Azimuth Check (SAM-T)
Squad Operations Orders
Written Exams (Fire Team Based)
14FEB56 (FRI):
No Work (President’s 4-Day)
15FEB56 (SAT):
No Work (President’s 4-Day)
09FEB56 (SUN):
No Work (Weekend)
AS OF DATE: 15JAN56
Timeline Sheet(s).
The next nine pages outline a day-by-day and hour-by-hour timeline for this event. This is an extensive collective event that demands a daily timeline in order to effectively coordinate resupply and general resourcing.
Notes: Concept (IWTS SQD Table I)
All Individual Tasks and Team Collective are trained throughout JAN20-FEB20 over a course of seven weeks.
09-15FEB is used to train-validate team collective tasks, administer written exams, and release the Virtual Trainer OPORD.
Platoons/Squads brief their Virtual Trainer OPORDs this week.
Leaders conduct an azimuth check on the next Week’s (Table II) Virtual Trainer.

## Slide 5
INDIVIDUAL-TEAM TRAINING (IWTS TABLE I) MICRO
10FEB56 (MON):
0630-0745 PRT
0900-1000 CO OPORD 01 (to PLT) with PLT Back-briefs (LFX Training OPORD)
1300-1500
Range Cadre Azimuth Check
SAM-T Visit Azimuth Check
(Focus on regularly scheduled command maintenance)
Section personnel focus:
Maintenance
AS OF DATE: 15JAN56
11FEB56 (TUE):
0630-0745 PRT
0900-1130 Fire Team Collective Training Exercises (Local training area lanes)
Priorities:
Reconnaissance
Maneuver
Route Planning
1300-1700 Fire Team Collective Training Exercises (cont.)
1300-1700 Platoon OPORD brief window (Crawl-Walk)
(MSTC Medical Training to occur simultaneously this day. Team training can occur around this scheduled event.)
12FEB56 (WED):
0630-0745 PRT
0900-1130 Fire Team Collective Training Exercises (Local training area lanes)
Priorities:
Reports
Communicating
Fire Control
1300-1700 Fire Team Collective Training Exercises (cont.)
1300-1700 Squad OPORD brief window. (Crawl-Walk)
(CBRNE & Hand Grenade Training to occur simultaneously this day. Team training can occur around this scheduled event.)
13FEB56 (THU):
0630-0745 PRT
0900-1130 Fire Team Collective Training Exams
Test Exam
Individual Exam
(Exams are time based and focus on fundamentals).
1300 Training Meeting (SQD STX-LFX Focused)
OCIE Layouts
1300 CO OPORD 02 (to PLT) with PLT Back-briefs (FoF OPORD)
(Hand Grenade Training to occur simultaneously this day. Team training can occur around this scheduled event.)
Notes: Concept (IWTS SQD Table I)
Day by Day Hourly Breakdown
Concept: This week will consist of squad led/platoon supervised fire team training with a culminating exam at the end of the week. This week will also require the leadership to lock in the Squad Leader/Team Leader personnel that will qualify through Table VI during the LFX.
SL
TLP & OPORD
LDR Recon 6-4 FM 3-21.8
Fire Team
Reconnaissance: 3-67 STP 7-11B1, 6-41 FM 3-21.8 (6-4 Ldr Recon), TEO 071-410-0010
Maneuver: 3-47 SPT 7-11B1, 3-12 STB 7-11B24
Route Planning: 5-9 FM 3-21.8, Ranger Handbook
Reports: SITREP, MEDVAC, RESUP, LACE, GOTWA
Communication: ASIP, Hand&Arm, PEQ-15 & Similar, FoxTail, ChemLight, MBTR, Runner(+Route)
Fire Control: Direct & Indirect Wpns Control (Ammo Rates, Distance, Integration, Effects of Terrain/Wtx, Uses on types of ENY)
AAR.
- Four day week complicates the ability to focus on Fire Team training. Avoid four days or plan to increase the training length when you cannot avoid them.
- Various training (MSTC, CBRNE, Hand Grenade) made it difficult to focus the company effort on any single event. The company was still capable of training the standard but not focus the entire company at any one time on one training task. One thing was noticed, overlaying multiple events in one week created a sort of unintended rotation effect between Soldiers from one event to the next. Soldiers prioritized for the M4 Range (BN Makeup Range) would complete the range prior to moving to another range, the CBRNE chamber and Decon stations. The planned events turned into pseudo stations of a sort. It may be helpful to plan mass training events all as a sort of training station rotation. This would be very similar to events decades ago that created stations for common individual and crew/team training stations. We could create a sheet that would require a Cadre member to certify they’d been to that individual station throughout the week. This would also enable an EIB approach to stations combined with other required annual individual training.
- Need more OPORD formal blocks of instruction. There was very little time to conduct these blocks of instruction around the nature of so much individual training occurring. If it can occur it needs to be more deliberate. No formal company TLP-OPORD classes were conducted during this week as intended.
- Need a better way of monitoring the 6x intended types of Fire Team training prior to Fire Teams taking exams. The Fire Teams could be tied more into the plan behind this training path and then asked to back-brief leadership on this training design to see if they’ve absorbed the intent and general training scheme prior to it occurring.
- Recommend having a block of instruction the week prior to the three week progression to all key players to really discuss the intent behind the training and require all key players to back brief in some fashion in order to ensure understanding of intent.
- Fire Team Exams. The exams appear to be a great tool to reveal what the Fire Teams knowledge is of common skills associated with individual and team tasks. These exams need to be adjusted to ensure the mechanized squads are answering tactically about not only the squad but the squads incorporation with the IFV and Tank.
- MCoE. The Army needs to provide exams as a standard practice for these progression type tables. For all MOSs. Engage MCoE as the first step on this.

## Slide 6
TEAM/SQUAD TRAINING (IWTS TABLE II)
17FEB56 (MON):
No Work (President’s 4-Day)
18FEB56 (TUE):
PRT
Command Maintenance
Leader/OC Azimuth Check (SAM-T)
SAM-T Senior Leader RXL
SAM-T Squad Leader Introduction
19FEB56 (WED):
PRT
Squad Virtual Trainer
- 2hr Lane Iterations
- Virtual Day Iterations
- 0900hrs-1900hrs
20FEB56 (THU):
PRT
Squad Virtual Trainer
- 2hr Lane Iterations
- Virtual Night Iterations
- 0900hrs-1900hrs
21FEB56 (FRI):
PRT
SAM-T Alibi Training & AAR
- Integrate AAR into training packet
Leader/OC Azimuth Check (STX-LFX)
OPORD (25FEB56 Operation) Release
22FEB56 (SAT):
No Work
16FEB56 (SUN):
No Work (President’s 4-Day)
AS OF DATE: 15JAN56
Notes: Concept (IWTS SQD Table II)
Table II is administered at the FRKS SAM-T Facility.
19FEB is the virtual day trainer, 2hr squad iterations, running from 0900-1900hrs.
20FEB is the virtual night trainer, 2hr squad iterations, running from 0900-1900hrs.
Virtual Trng consolidated training plan AAR is completed 21FEB
25FEB STX Operation OPORD is released 21FEB19

## Slide 7
TEAM/SQUAD TRAINING (IWTS TABLE II) MICRO
18FEB56 (TUE):
PRT 0630-0745
Key Leader Rxl
0900 Arrive SAM-T for Rxl
0900-1100 SAM-T Cadre Rxl
0900-1500 PLT OPORD Brief Window (FoF)
(Focus on regularly scheduled command maintenance)
Section personnel focus:
Maintenance
SAM-T Reservation (18-21)
AS OF DATE: 15JAN56
19FEB56 (WED): SAM-T 1PLT
PRT 0630-0745
0900-1530 1PLT @ SAM-T
30-40min lane interval trng.
Priorities:
- 6x Fire Team focus points (week prior focus)
0900-1600 2PLT-3PLT SQD Training Local Area
- 6x training focus points (week prior focus)
Non-lane fire teams will observe lane training for Lessons Learned, Rehearse prior to lane execution, and conduct retraining and dialogue with best practices.
0900-1500 SQD OPORD Brief Window (FoF)
Section personnel focus:
Maintenance
20FEB56 (THU): SAM-T 2PLT
PRT 0630-0745
0900-1530 2PLT @ SAM-T
30-40min lane interval trng.
Priorities:
- 6x Fire Team focus points (week prior focus)
0900-1600 1PLT-3PLT SQD Training Local Area
- 6x training focus points (week prior focus)
Non-lane fire teams will observe lane training for Lessons Learned, Rehearse prior to lane execution, and conduct retraining and dialogue with best practices.
0900-1600 PLT Re-Brief with improved products window (FoF)
Section personnel focus:
Maintenance
21FEB56 (FRI): SAM-T 3PLT
PRT 0630-0745
0900-1530 3PLT @ SAM-T
30-40min lane interval trng.
Priorities:
- 6x Fire Team focus points (week prior focus)
0900-1600 1PLT-2PLT SQD Training Local Area
- 6x training focus points (week prior focus)
Non-lane fire teams will observe lane training for Lessons Learned, Rehearse prior to lane execution, and conduct retraining and dialogue with best practices.
0900-1600 PLT Re-Brief with improved products window (FoF)
1300 CO OPORD 03 (to PLT) with PLT Back-briefs (LFX OPORD)
Section personnel focus:
Maintenance
Notes: Concept (IWTS SQD Table II)
Day by Day Hourly Breakdown
Concept: Leadership will visit the site the week prior (10FEB) and the week of (18FEB) to do a site walk-through and then a full RXL. Each platoon will have a day to conduct this training. The days not conducting training at the site will be spent watching or conducting COF/Local Trng Area trng.
Integrate 6x Learning Focal Points from GST Table I
AAR
- The Fire Teams and higher level leadership really enjoyed the SAM-T trainer. The ability to focus on fundamentals that were stressed during the prior week but in-action was a real big asset with this particular virtual trainer. The Soldiers enjoyed the ability to fire weapon systems standing aligned as a fire team… able to give fire commands, maneuver (although limited by a small 25m squad space approx.), and peform basic battle drill actions while being coached by senior leaders, primarily the fire team’s squad leader and platoon sergeant. The 1SG and CDR visited training to interact with senior leaders and Soldiers and understand the effects of this training regimen.
- Maintenance by Crews and minimal training distractors greatly enabled the squads to perform within this virtual trainer and prepare for the field exercise prior to heading to the field the next week.
- Need to consider an off-virtual trainer day focus for platoons … that while vaguely mentioned not specifically designed so creativity could be a type of burden on the squad to figure out training methods or general focus when not scheduled for virtual training.
- Deliberate equipment inspections need to be planned this week prior to field departure the next week.
- A Cadre focus brief to check azimuth on the total training plan was conducted the Thursday in place of the normal company training meeting. This was useful and identified sizeable flaws in planning/coordination gaps. Recommend conducting one of these IPR type meetings the week prior as well… and maybe not involve so many players until the week of.
- A more deliberate OC-Academy needs to be held the week prior. An brief OC outline was given during the Cadre Brief on Thursday this week.. And while decent.. Could have been better.
- HQ setup the Company-Cadre Tent and rehearsed the CP operations and expectations for running the lanes the next week. This could have been a bit more deliberate and involved more key players like the OIC and RSO

## Slide 8
SQUAD TRAINING (IWTS TABLE III-VI)
24FEB56 (MON):
PRT (Reschedule to Field PRT)
NLT 0900 (Company @ Range 53-54)
Safety Brief / Range Orientation
NLT 1200 SQD AA’s Established
PLT OPORD Briefs (0900-1200)
SQD OPORD Briefs (1200-1900)
25FEB56 (TUE) (Tbl III-IV) (FoF):
DAY First Lane SP 0700hrs
2hr Iterations / 5x Iterations
Last SP 1700hrs (27FEB FRAGO)
NIGHT First Lane SP 1900hrs
1.5hr Iterations / 5x Iterations
Last SP 0230hrs
26FEB56 (WED) (Tbl III-IV) (FoF):
DAY First Lane SP 0700hrs
2hr Iterations / 5x Iterations
Last SP 1700hrs (28FEB FRAGO)
NIGHT First Lane SP 1900hrs
1.5hr Iterations / 5x Iterations
Last SP 0230hrs
27FEB56 (THU) (Tbl V-VI) (LFX):
DAY First Lane SP 0700hrs
2hr Iterations / 5x Iterations
Last SP 1700hrs
NIGHT First Lane SP 1900hrs
1.5hr Iterations / 5x Iterations
Last SP 0230hrs
28FEB56 (FRI) (Tbl V-VI) (LFX):
DAY First Lane SP 0700hrs
2hr Iterations / 5x Iterations
Last SP 1700hrs
NIGHT First Lane SP 1900hrs
1.5hr Iterations / 5x Iterations
Last SP 0230hrs
29FEB56 (SAT) (Tbl V-VI) (LFX):
DAY First Lane SP 0700hrs
2hr Iterations / 5x Iterations
Last SP 1700hrs
NIGHT First Lane SP 1900hrs
1.5hr Iterations / 5x Iterations
Last SP 0230hrs
01MAR56 (SUN):
Alibi Day-Night Lanes (5x Iterations ea)
Range Closeout
Consolidated Training Plan AAR
100% SI Check
NLT 0400 Training Complete
(1st WK March, AAR & Recovery)
02-06MAR56 (Recovery)
07-15MAR56 (Leave Window)
23FEB56 (SUN):
No Work
AS OF DATE: 15JAN56
Notes: Concept (IWTS SQD Table III-VI)
Tables III-VI are completed at FRKS Ranges 53-54.
24FEB is the initial site establishment, azimuth check, and safety brief
25-26FEB are the day-night iterations for up to 20 squads, Force on Force, TADSS, training in M2C, Attack & Defense Simultaneously.
27-29FEB are the day-night iterations for up to 9 squads, Day01 Dry, Day02-03 Live, training in M2C, Attack & Defense Simultaneously.
01MAR can accommodate additional LFX alibis for those requiring retraining.

## Slide 9
SQUAD TRAINING (IWTS TABLE III-VI) MICRO
24FEB56 (MON): SQD DAY 0
Chow: M/M/H
FIRST CALL (COF) 0500hrs
SQDs est AAs (RG 53) 0850hrs
CADRE est CP (RG 53) 0800hrs
Safety Brief 0900hrs @ CP
Key Leader Rxls
1100 Lane Walk Rxl
1300 Cadre Comms Rxl
1500 Cadre Emergency Rxl
1000-1600 SQD OPORD Window
Section personnel not service as Cadre focus:
Maintenance
SAM-T Reservation (18-21)
AS OF DATE: 15JAN56
24FEB56 (MON): (cont.)
Objectives.
- Establish Company CP and Squad AAs. Company CP will function as the Cadre CP during training but exercise full CP operations.
- Squads brief & re-brief OPORDs to standard.
- Squads conduct RXLs and Reconnaissance to standard.
- Squads conduct reporting to standard.
25FEB56 (TUE): SQD DAY 1
Chow: H/M/H
0700-0200 SQD FoF Iterations
2hr iterations with 1hr reset between for AAR and movement to-from. Each Iteration will train 2x Squads.
Total Train Day/Night 6 SQDs
0700-1000 Iteration 01 FoF
1000-1300 Iteration 02 FoF
1300-1600 Iteration 03 FoF
1600-1900 Iteration 04 FoF
(Semi-Night)
1900-2200 Iteration 05 FoF
(Night)
2200-0100 Iteration 06 FoF
(Night)
1500 SQD LFX FRAGORD Release by Cadre
25FEB56 (TUE): (cont.)
Objectives.
Squad 6x Focus Points
Cadre.
PL/PSG Lane grader per SQD
CDR Evaluator
1SG sustainment effort
CO CP Risk Mgmt
LFX Preparation.
Cadre Lane Confirmation
Live Safety Pre-Brief
Road Block Confirmation
Notes: Concept (IWTS SQD Table III-VI)
Day by Day Hourly Breakdown
AAR
- Change the force on force to a more OPFOR based direction for STX. This is because of the lack of MILES and coordination + general lack of understanding with the complexities of having two squads simultaneously maneuver on one another. I’m not sure which method works better. We will see. A squad on squad concept would definitely engage squads more and get more squads through STX training at a higher rate than just placing one squad against an OPFOR…. But the Army isn’t used to doing training this way… facing off with yourself. This needs to be attempted in the future with more deliberate planning.

## Slide 10
SQUAD TRAINING (IWTS TABLE III-VI) MICRO
26FEB56 (WED): SQD DAY 2
Chow: H/M/H
0500 Safety Brief
(BLANK TABLE IV-V)
2hr blank iterations with 1hr reset between for AAR and movement to-from. Each Iteration will train 1x Squad. 3 SQDs trained.
0700-1000 Iteration 01
1000-1300 Iteration 02
1300-1600 Iteration 03
1600-1900 Iteration 04 (Night)
1900-2200 Iteration 05 (Night)
2200-0100 Iteration 06 (Night)
1500 SQD LFX FRAGORD Release by Cadre
Section personnel not service as Cadre focus:
Maintenance
AS OF DATE: 15JAN56
26FEB56 (WED): (cont.)
Objectives.
Squad 6x Focus Points
Cadre.
PL/PSG Lane grader per SQD
CDR Evaluator
1SG sustainment effort
CO CP Risk Mgmt
27FEB56 (THU): SQD DAY 3
Chow: H/M/H
0500 Safety Brief
(BLANK TABLE IV-V)
2hr blank iterations with 1hr reset between for AAR and movement to-from. Each Iteration will train 1x Squad. 3 SQDs trained.
0700-1000 Iteration 01
1000-1300 Iteration 02
1300-1600 Iteration 03
1600-1900 Iteration 04 (Night)
1900-2200 Iteration 05 (Night)
2200-0100 Iteration 06 (Night)
1500 SQD LFX FRAGORD Release by Cadre
Section personnel not service as Cadre focus:
Maintenance
27FEB56 (THU): (cont.)
Objectives.
Squad 6x Focus Points
Cadre.
PL/PSG Lane grader per SQD
CDR Evaluator
1SG sustainment effort
CO CP Risk Mgmt
LFX Preparation.
Cadre Lane Confirmation
Live Safety Pre-Brief
Road Block Confirmation
Notes: Concept (IWTS SQD Table III-VI)
Day by Day Hourly Breakdown

## Slide 11
SQUAD TRAINING (IWTS TABLE III-VI) MICRO
28FEB56 (FRI): SQD DAY 4
Chow: H/M/H
0500 Safety Brief
(LIVE TABLE VI)
2hr live iterations with 1hr reset between for AAR and movement to-from. Each Iteration will train 1x Squad. 3 SQDs trained.
0700-1000 Iteration 01
1000-1300 Iteration 02
1300-1600 Iteration 03
1600-1900 Iteration 04 (Night)
1900-2200 Iteration 05 (Night)
2200-0100 Iteration 06 (Night)
1500 SQD LFX FRAGORD Release by Cadre
Section personnel not service as Cadre focus:
Maintenance
AS OF DATE: 15JAN56
28FEB56 (FRI): (cont.)
Objectives.
Squad 6x Focus Points
Cadre.
PL/PSG Lane grader per SQD
CDR Evaluator
1SG sustainment effort
CO CP Risk Mgmt
29FEB56 (SAT): SQD DAY 5
Chow: H/M/H
0500 Safety Brief
(LIVE TABLE VI)
2hr live iterations with 1hr reset between for AAR and movement to-from. Each Iteration will train 1x Squad. 3 SQDs trained.
0700-1000 Iteration 01
1000-1300 Iteration 02
1300-1600 Iteration 03
1600-1900 Iteration 04 (Night)
1900-2200 Iteration 05 (Night)
2200-0100 Iteration 06 (Night)
1500 SQD LFX FRAGORD Release by Cadre
Section personnel not service as Cadre focus:
Maintenance
29FEB56 (SAT): (cont.)
Objectives.
Squad 6x Focus Points
Cadre.
PL/PSG Lane grader per SQD
CDR Evaluator
1SG sustainment effort
CO CP Risk Mgmt
Notes: Concept (IWTS SQD Table III-VI)
Day by Day Hourly Breakdown

## Slide 12
SQUAD TRAINING (IWTS ALIBI & RECOVERY) MICRO
01MAR56 (SUN): SQD DAY 6
Chow: H/M (RTB for Dinner)
ALIBI/RETRAIN DAY
0500 Safety Brief
(LIVE TABLE VI)
2hr live iterations with 1hr reset between for AAR and movement to-from. Each Iteration will train 1x Squad. 3 SQDs trained.
0700-1000 Iteration 01
1000-1300 Iteration 02
1300-1500 Range Clearance
1700 NLT COF Release
AS OF DATE: 15JAN56
01MAR56 (SUN): (cont.)
Objectives.
Squad 6x Focus Points
Cadre.
PL/PSG Lane grader per SQD
CDR Evaluator
1SG sustainment effort
CO CP Risk Mgmt
02-06MAR56
Recovery
Release @ 1600hrs
Squad Deliberate Recovery Plan
OCIE
Weapons
Optics
AAR Comment Submittal
Retrain Classroom Dialogue
Maneuver and Navigation AAR
TTPs & SOP AAR
Crews
Vehicle Maintenance (Normally Scheduled)
Spring Break Risk Mitigation Classes
07-15MAR56
Spring Break
Notes: Concept (IWTS SQD ALIBI-RECOVERY)
Day by Day Hourly Breakdown

## Slide 13
FORCE ON FORCE EXERCISE (SQUAD)
LABEL | GRID
01 (CP) | 78S PK 25870 43083
01 (MEDIC) | “
01 (AXP) | “
01 (SAFETY BRF) | “
02 (AA1 FoF) | 78S PK 25870 43083
13 (AA2 FoF) | 78S PK 25870 43083
03 (ORP1 FoF) | 78S PK 25870 43083
05 (ORP2 FoF) | 78S PK 25870 43083
Moderate vegetation, gently rolling terrain, minimal unimproved roads
Winter conditions; open vegetation and increased visibility.
High 55 / Low 30, Winds approx. 10-20mph, SR ~0715, SS ~1800. Slight precipitation for the month of February.
Lane Concept: Days 01-02. Force on Force places squad against squad. Each squad will SP from their AA (Area 02 & Area 13) after conducting TLPs and emplace in their ORP (Area 03 & Area 04). After completing reconnaissance the squads will maneuver towards enemy defenses and seize each other’s defense. These iterations will last approx. 1.5-2hrs each. This is the unit’s Table III TADSS exercise. An Enemy templated recon will be briefed at 78S PK 25870 43083 in order to assist with keeping units within a designated boundary.
MAP WITH POINTS DEPICTED HERE
Imagery Sheet(s).
These two pages depict an imagery sheet that shows important administrative locations against the training area upon which the training will be conducted.

## Slide 14
LIVE FIRE EXERCISE (SQUAD)
LABEL | GRID
01 (CP) | 78S PK 25870 43083
01 (MEDIC) | “
01 (AXP) | “
01 (SAFETY BRF) | “
02 (AA LFX) | 78S PK 25870 43083
05 (ORP LFX) | 78S PK 25870 43083
06 (ENY RECON) | 78S PK 25870 43083
07 (Bunker 01) | 78S PK 25870 43083
08 (Bunker 02) | 78S PK 25870 43083
09 (Bunker 03) | 78S PK 25870 43083
10 (Bunker 04) | 78S PK 25870 43083
11 (Bunker 05) | 78S PK 25870 43083
12 (Bunker 06) | 78S PK 25870 43083
14 (AT-4 FP) | 78S PK 25870 43083
Moderate vegetation, gently rolling terrain, minimal unimproved roads
Winter conditions; open vegetation and increased visibility.
High 55 / Low 30, Winds approx. 10-20mph, SR ~0715, SS ~1800. Slight precipitation for the month of February.
Lane Concept: Days 03-06. Live fire exercises both Table V and VI. Each squad will SP from their AA located vic Area 02 after conducting TLPs and emplace in their ORP vic Area 05 during their iteration (day and night). After completing reconnaissance the squad will maneuver towards seizing a bunker at Area 09 or Area 10 depending on the COA, OPORD and effects from simulated BN Mortars. They will encounter enemy dismount targets (enemy 2-3 man reconnaissance) at Area 06. SBF and Assault fire teams will destroy their bunker and set a hasty defense where they will engage 1x armored target south of their bunker prior to receiving a change of mission (AT-4 Area 14). This will complete their iteration (1.5-2hrs). Areas 07-08 and 11-12 are non-engaged bunkers constructed to represent a larger defense.
MAP WITH POINTS DEPICTED HERE